## Summary
BRD Creation |  |  |  |  | BRD Approval
Count of Name | Status |  |  |  | Count of Name | Status2
Domain | In Progress | Planned | (blank) | Grand Total | Domain | (blank) | Planned | Grand Total
(blank) |  |  |  |  | (blank)
Enrollment | 2 | 10 |  | 12 | Enrollment |  | 12 | 12
Daily Census (ADT) |  | 6 |  | 6 | Daily Census (ADT) | 1 | 5 | 6
Claims |  | 4 |  | 4 | Claims | 4 |  | 4
Grand Total | 2 | 20 |  | 22 | Grand Total | 5 | 17 | 22

## BRD Plan
[5 empty] | BRD/Infra Creation |  |  |  |  | BRD Approved
# | Domain | Source/Extract/Integration | Name | Technology | Task | Owner | Status | Start Date | End Date | Owner | Status | Start Date | End Date
1 | Enrollment | Source Ingestion | Fedelis NY Upstate | Stored Procedure | BRD Creation | Syed | In Progress | 13/3/2026 | 20/3/2026 |  | Planned
2 | Enrollment | Source Ingestion | Fedelis NY downstate | Stored Procedure | BRD Creation | Syed | In Progress | 13/3/2026 | 20/3/2026 |  | Planned
3 | Enrollment | Source Ingestion | Molina NY | Stored Procedure | BRD Creation | Syed | Planned | 2026-03-16 | 21/3/2026 |  | Planned
4 | Enrollment | Source Ingestion | Optum NY(Manual) | Stored Procedure | BRD Creation | Syed | Planned | 2026-03-16 | 21/3/2026 |  | Planned
5 | Enrollment | Source Ingestion | Centene GA | Stored Procedure | BRD Creation | Syed | Planned | 2026-03-16 | 21/3/2026 |  | Planned
6 | Enrollment | Source Ingestion | Centene IL | Stored Procedure | BRD Creation | Syed | Planned | 2026-03-16 | 21/3/2026 |  | Planned
7 | Enrollment | Source Ingestion | Athena (Legacy Grace at Home) | Stored Procedure | BRD Creation | Syed | Planned | 21/3/2026 | TBF |  | Planned
8 | Enrollment | Source Ingestion | CAH_152 (HRSAC4M) | Stored Procedure | BRD Creation | Syed | Planned | 21/3/2026 | TBF |  | Planned
9 | Enrollment | Source Ingestion | CMP_1598 | Stored Procedure | BRD Creation | Syed | Planned | 21/3/2026 | TBF |  | Planned
10 | Enrollment | Source Ingestion | D0284 | Stored Procedure | BRD Creation | Syed | Planned | 21/3/2026 | TBF |  | Planned
11 | Enrollment | Source Ingestion | MSSP | Stored Procedure | BRD Creation | Syed | Planned | 21/3/2026 | TBF |  | Planned
12 | Enrollment | Integration | Verato Extraction | C# | BRD Creation | Syed | Planned | 21/3/2026 | TBF |  | Planned
13 | Daily Census (ADT) | Source Ingestion | ADF to Cinq DB | ADF | BRD Creation | Monica | Planned
14 | Daily Census (ADT) | Integration | Fedilis NY | ADF | BRD Creation | Monica | Planned | 2026-03-16 | 2026-03-20 |  | Planned
15 | Daily Census (ADT) | Integration | Rhio | ADF | BRD Creation | Monica | Planned | 2026-03-16 | 2026-03-20 |  | Planned
16 | Daily Census (ADT) | Integration | Particle Health | ADF | BRD Creation | Monica | Planned | 2026-03-16 | 2026-03-20 |  | Planned
17 | Daily Census (ADT) | Integration | Garage | ADF | BRD Creation | Monica | Planned | 2026-03-16 | 2026-03-20 |  | Planned
18 | Daily Census (ADT) | Integration | PCC | ADF | BRD Creation | Monica | Planned | 2026-03-16 | 2026-03-20 |  | Planned
19 | Claims | Source Ingestion | Centene |  | BRD Creation | Aysha | Planned | 2026-03-16 | 2026-03-20
20 | Claims | Source Ingestion | Molina |  | BRD Creation | Aysha | Planned | 2026-03-23 | 2026-03-27
21 | Claims | Source Ingestion | Optum ECG |  | BRD Creation | Aysha | Planned | TBF | TBF
22 | Claims | Source Ingestion | CMS |  | BRD Creation | Aysha | Planned | TBF | TBF

## Infra Plan
# | Task | Owner | Status | Start Date | End Date
1 | Access to Azure infra
2 | Document existing infrastructure
3 | Document data lake Azure setup
4 | Docker images sync to Cinq environment
5 | Validate the permissions between services
6 | Data Lake environment - Setup prerequisties |  | Planned
7 | Data lake environment - Validate Key Vault & permissions |  | Planned
8 | Data lake environment - Setting up the database |  | Planned
9 | Data lake environment -Helm Chart Setup & configuration |  | Planned
10 | Data lake environment - Setting up the AKS |  | Planned
11 | Data lake environment - Setting up the databricks |  | Planned
12 | Data lake environment - Github for infrastructure |  | Planned
13 | Data lake environment - Github for application code |  | Planned
14 | Data lake environment - Setting up github actions |  | Planned