## Slide 1
Data Lakehouse Phase 1 Execution Plan
Prepared for COO, CFO, Chief Legal Officer, IT Leadership, and Program Owners — March 11, 2026

## Slide 2
Objective & Commitment
Objective
Stand up a governed operational insight layer using only ADT, claims, and eligibility roster data. Phase 1 is complete when trusted outputs are in use, not when a broad platform build is finished.
Commitment
By mid-May 2026, deliver four production outputs supported by defined owners, refresh schedules, reconciliation controls, and a clear handoff from the outsourced team to internal IT, analytics, and business owners.

## Slide 3
Purpose & Scope
This document defines the executable Phase 1 plan for the Data Lakehouse workstream. It is written for internal turnover and decision-making — not to re-sell the program. It clarifies what Phase 1 will deliver, what it will not deliver, what internal resources are required, and how the outsourced team will transfer knowledge.
Phase 1 scope is intentionally limited to three source domains: ADT, claims, and eligibility rosters. No additional data domains are required.

## Slide 4
Phase 1 Outcome: Definition of Done
Phase 1 is complete when all of the following are true:
Four Outputs Live
All four production outputs are available to named business and operational owners, using only ADT, claims, and eligibility data.
Documented & Operating
Refresh cadence, ownership, and reconciliation rules are documented and actively operating.
Internal Teams Self-Sufficient
Internal teams can explain data flow, transformation logic, quality checks, and the support model without dependence on the outsourced team.
Agreed Backlog Exists
A documented backlog covers deferred work, Phase 1.5 hardening, and later source expansion.

## Slide 5
Phase 1 Production Outputs
1
Acute Event Command View
Daily view of admissions, discharges, and ED events for operational awareness. Uses ADT + current eligibility match. Owner: Operations.
2
Transition of Care Action Layer
Workable output for attributed members with recent acute events requiring follow-up. Uses ADT, eligibility, and selected claims. Owner: Clinical Operations.
3
High Utilization & Cost Pressure View
Current attributed members with recent inpatient, repeat ED, or high-cost patterns. Uses claims + current eligibility. Owner: Finance & Operations.
4
Data Quality & Reconciliation Control Layer
Visibility into stale feeds, unmatched records, roster gaps, and output trust issues. Uses ADT, claims, eligibility, and transformation checks. Owner: IT & Analytics.

## Slide 6
What Is Out of Scope
No New Sources
No source onboarding beyond ADT, claims, and eligibility rosters.
No Canonical Modeling
No enterprise-wide modeling beyond what supports the four Phase 1 outputs.
No Backfill
No historical backfill beyond the minimum required to make outputs useful.
No Generic Frameworks
No ingestion framework buildout for future sources.
No AI/ML Workloads
No advanced AI feature engineering, model development, or new data science workloads.
No Dashboard Redesign
No dashboard work that does not improve trust, actionability, or reuse.

## Slide 7
Internal Resource Model
The outsourced team accelerates current-state understanding and establishes governed data products. Internal teams must be staffed to absorb knowledge and own the environment after go-live.
Role
Primary Responsibility
Internal FTE
Outsourced FTE
Executive Sponsor
Scope protection, escalation, decisions
0.1
As needed
Business Product Owner
Output definitions, acceptance, prioritization
0.5
Support only
Technical Delivery Lead
Integrated execution across teams
0.75
0.5
Analytics Lead
Metric definition, output validation
0.5
0.25
Data Engineering Lead
Pipeline and transformation ownership
1.0
1.0
ADT / Claims / Eligibility Source Owners
Source validation and defect resolution
0.25 each
0.25 each
Critical: If named internal roles are not ring-fenced for Phase 1, the outsourced team will function as a temporary overlay rather than an accelerator with a usable handoff.

## Slide 8
Knowledge Transfer & Current State Understanding
Transfer Objectives
Document current-state data flow for ADT, claims, and eligibility from source through transformation, reporting, and issue handling.
Identify where Power BI outputs rely on duplicated logic, manual reconciliation, or undocumented business rules.
Establish one agreed set of business definitions and reconciliation rules for all four outputs.
Ensure internal teams can validate scope, accept deliverables, and support outputs after go-live.
Required Deliverables from Outsourced Team
Current-state architecture diagram and field-level source map.
Transformation inventory: existing logic, duplicates, and retirement candidates.
Data quality and reconciliation rules per output.
Runbook: refresh cadence, defect triage, monitoring, and escalation.
Walkthrough sessions with recorded demos and written handoff materials.

## Slide 9
Delivery Plan
1
Week 1
Freeze Phase 1 scope and internal assignments. Deliver approved output list, owner matrix, and source boundary. Owner: Executive Sponsor
2
Week 2
Complete current-state assessment and source field map. Deliver architecture diagram, field map, and known gaps. Owner: Technical Delivery Lead
3
Week 3
Finalize business definitions and reconciliation rules. Deliver metric definitions, matching logic, and refresh rules. Owner: Business Product Owner
4
Weeks 4–5
Build and validate governed transformation layer. Deliver initial output datasets and reconciliation results. Owner: Data Engineering Lead
5
Weeks 6–7
Validate with internal users and stabilize defects. Deliver signed output validation and updated runbooks. Owner: Analytics Lead
6
Weeks 8–9
Move outputs into production cadence and complete handoff. Deliver production run, monitoring, and support readiness. Owner: Technical Delivery Lead

## Slide 10
Governance & Working Cadence
Accountability Structure
Executive Sponsor
Scope protection, escalation, and cross-functional decisions.
Business Product Owner
Acceptance of four outputs, defect prioritization, and operating alignment.
Technical Delivery Lead
End-to-end execution across internal and outsourced resources.
Analytics Lead
Output usability, metric definitions, and validation against current reporting.
Data Engineering Lead
Pipelines, transformations, quality controls, and support readiness.
Meeting Cadence
Daily 20-min standup — active execution issues
Twice-weekly working session — architecture, logic, and reconciliation decisions
Weekly executive checkpoint — scope, risk, staffing, and acceptance readiness
Weekly KT checkpoint — internal readiness and open gaps

## Slide 11
Risks & Dependencies
Uncontrolled Scope Growth
Delays delivery and weakens knowledge transfer. Control: No new sources or use cases without executive approval.
Insufficient Internal Staffing
Creates dependence on outsourced team after go-live. Control: Ring-fence internal roles; require attendance in transfer sessions.
Undefined Business Logic
Creates conflicting outputs and weak trust. Control: Lock business definitions before transformation completion.
Source Quality & Matching Issues
Creates reconciliation failures and user distrust. Control: Publish data quality controls and exception handling with each output.
Competing Operational Priorities
Pulls internal owners away from acceptance and handoff. Control: Weekly executive checkpoint to enforce priority and remove blockers.

## Slide 12
Decisions Required Now
Confirm Scope Boundary
Phase 1 remains limited to ADT, claims, and eligibility rosters only.
Approve Four Outputs
The four Phase 1 outputs are the only required production deliverables for mid-May 2026.
Assign & Ring-Fence Roles
Assign and protect the internal roles identified in this plan.
Require KT Artifacts
Require the outsourced team to deliver all knowledge transfer and current-state artifacts listed in this plan.
Defer Expansion
Defer any additional source expansion or generalized platform work to a later phase.

## Slide 13
APPENDIX
Phase 1 Output Definitions
1. Acute Event Command View
Current admissions, discharges, and ED activity matched to the current attributed population for operational awareness and prioritization.
2. Transition of Care Action Layer
Action-oriented view of attributed members with recent acute events requiring follow-up, with timing, assignment, and unresolved exception visibility.
3. High Utilization & Cost Pressure View
Claims plus roster-driven view of attributed members with elevated recent inpatient, repeat ED, or cost pressure patterns.
4. Data Quality & Reconciliation Control Layer
Visibility into source freshness, unmatched records, roster alignment issues, and reconciliation exceptions that affect trust in the outputs.